## Release Plan 20240730
Release Plan 20240730
Date
Create & Freeze Release Branch: | Friday, July 26, 2024
Release Planned Date: | Tuesday, July 30, 2024
Project/Repositories | Release Version | Create Release Branch | Deploy Release to PP | Merged Release to Master | Production Deployment | Release/Tagging | Merge Release to Develop | Deploy Develop to PP | Remarks | Jenkins Paste
commons | 1.5.205-SNAPSHOT | [8 empty] | commons=1.5.206-SNAPSHOT
Back End | [9 empty] | Back End=
psi-service | release-8.81 | [8 empty] | psi-service=release-8.81
wqs-service | release-1.0.76 | [8 empty] | wqs-service=release-1.0.76
aims-service | release-5.2.1 | [8 empty] | aims-service=release-5.2.1
irp-service | release-8.81 | [8 empty] | irp-service=release-8.81
Front End | [9 empty] | Front End=
aca | release-1.12.39 | [8 empty] | aca=release-1.12.39
irp-web | release-8.81 | [8 empty] | irp-web=release-8.81
psi-web | release-8.81 | [8 empty] | psi-web=release-8.81
public-api | release-1.2.186 | [8 empty] | public-api=release-1.2.186
back-office | release-8.79 | [8 empty] | back-office=release-8.79
aims-web | release-5.2.1 | [8 empty] | aims-web=release-5.2.1
exchange-console | release-1.2.1 | [8 empty] | exchange-console=release-1.2.1
checklist-web | release-8.79 | [8 empty] | checklist-web=release-8.79
EKS services | Deployment PR link | Release/Tagging Branch | Deploy Release to PP | Production Deployment | Remarks
claim
claim-cloud
aca-new
exchange-service-cloud
document-generation-service-cloud
user-service-cloud
sso-management
e-signature
qrcode-cloud

## Release Plan 20240723
Release Plan 20240723
Date
Create & Freeze Release Branch: | Tuesday, July 16, 2024
Release Planned Date: | Tuesday, July 23, 2024
Project/Repositories | Release Version | Create Release Branch | Deploy Release to PP | Merged Release to Master | Production Deployment | Release/Tagging | Merge Release to Develop | Deploy Develop to PP | Remarks | Jenkins Paste
commons | 1.5.204-SNAPSHOT | [8 empty] | commons=1.5.204-SNAPSHOT
Back End | [9 empty] | Back End=
B2B_DT_Service | release-0.162 | Complete | Complete | Complete | Complete |  |  |  |  | B2B_DT_Service=release-0.162
back-office | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | back-office=release-8.79
checklist-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | checklist-web=release-8.79
customer-service | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | customer-service=release-8.79
factory-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | factory-web=release-8.79
exchange-service-cloud | release-1.0.48 | Complete | Complete | Complete | Complete |  |  |  |  | exchange-service-cloud=release-1.0.48
exchange-worker-service-cloud | release-1.0.48 | Complete | Complete | Complete | Complete |  |  |  |  | exchange-worker-service-cloud=release-1.0.48
mail-console | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | mail-console=release-8.79
final-report-service | release-8.79 | Complete | Postponed | Postponed | Postponed |  |  |  |  | final-report-service=release-8.79
ip-service | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | ip-service=release-8.79
IPTB-service | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | IPTB-service=release-8.79
irp-service | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | irp-service=release-8.79
psi-service | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | psi-service=release-8.79
aims-service | release-5.1.9 | Complete | Complete | Complete | Complete |  |  |  |  | aims-service=release-5.1.9
document-service | release-5.1.9 | Complete | Complete | Complete | Complete |  |  |  |  | document-service=release-5.1.9
data-service | release-5.1.9 | Complete | Complete | Complete | Complete |  |  |  |  | data-service=release-5.1.9
Front End | [9 empty] | Front End=
ACA | release-1.12.37 | Complete | Complete | Complete | Complete |  |  |  |  | ACA=release-1.12.37
CIA-NEW | release-2.1.6 | Complete | Complete | Complete | Complete |  |  |  |  | CIA-NEW=release-2.1.6
gi-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | gi-web=release-8.79
Public-API | release-1.2.184 | Complete | Complete | Complete | Complete |  |  |  |  | Public-API=release-1.2.184
irp-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | irp-web=release-8.79
psi-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | psi-web=release-8.79
parameter-web | release-8.79 | Complete | Complete | Complete | Complete |  |  |  |  | parameter-web=release-8.79
aims-web | release-5.1.9 | Complete | Complete | Complete | Complete |  |  |  |  | aims-web=release-5.1.9
program-web | release-5.1.9 | Complete | Complete | Complete | Complete |  |  |  |  | program-web=release-5.1.9
EKS services | Deployment PR link | Release/Tagging Branch | Deploy Release to PP | Production Deployment | Remarks
qrcode-cloud |  |  | Postponed
qcore-common-front | https://jenkins.qima.com/job/Prod/job/prod-qcore-common-front/ |  | Complete |  | Complete
claim-cloud | https://jenkins.qima.com/job/Prod/job/prod-claim-cloud/ |  | Complete |  | Complete
finance-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1603 |  | Complete |  | Complete
file-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1605 |  | Complete |  | Complete
exchange-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1604 |  | Complete |  | Complete
exchange-worker-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1601 |  | Complete |  | Complete
claim | https://github.com/asiainspection/qcore-apps-descriptors/pull/1600 |  | Complete |  | Complete
aca-new | https://github.com/asiainspection/qcore-apps-descriptors/pull/1611 |  | Complete |  | Complete
lab-photo | https://github.com/asiainspection/qcore-apps-descriptors/pull/1596 |  | Postponed |  | Postponed
lt-external-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1612 |  | Complete |  | Complete
gi-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1607 |  | Complete |  | Complete
program-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1606 |  | Complete |  | Complete
payment-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1599 |  | Complete |  | Complete

## Release Plan 20240716
Release Plan 20240716
Date
Create & Freeze Release Branch: | Friday, July 12, 2024
Release Planned Date: | Tuesday, July 16, 2024
Project/Repositories | Release Version | Create Release Branch | Deploy Release to PP | Merged Release to Master | Production Deployment | Release/Tagging | Merge Release to Develop | Deploy Develop to PP | Remarks | Jenkins Paste
commons | 1.5.203-SNAPSHOT | [8 empty] | commons=1.5.203-SNAPSHOT
Back End | [9 empty] | Back End=
aims-service | release-5.1.8 | Complete | Complete | Complete | Complete |  |  |  |  | aims-service=release-5.1.8
back-office | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | back-office=release-8.78
customer-service | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | customer-service=release-8.78
irp-service | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | irp-service=release-8.78
psi-service | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | psi-service=release-8.78
Front End | [9 empty] | Front End=
ACA | release-1.12.36 | Complete | Complete | Complete | Complete |  |  |  |  | ACA=release-1.12.36
aims-web | release-5.1.8 | Complete | Complete | Complete | Complete |  |  |  |  | aims-web=release-5.1.8
gi-web | release-8.72 | Complete | Complete | Complete | Complete |  |  |  |  | gi-web=release-8.72
irp-web | release-8.75 | Complete | Complete | Complete | Complete |  |  |  |  | irp-web=release-8.75
parameter-web | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | parameter-web=release-8.78
psi-web | release-8.78 | Complete | Complete | Complete | Complete |  |  |  |  | psi-web=release-8.78
sample-web | release-8.69 | Complete | Complete | Complete | Complete |  |  |  |  | sample-web=release-8.69
EKS services | Deployment PR link | Release/Tagging Branch | Deploy Release to PP | Production Deployment | Remarks
dynamic-order-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1573 | Completed | Completed | Completed
exchange-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1574 | Completed | Completed | Completed
exchange-worker-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1575 | Completed | Completed | Completed
parameter-service-legacy-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1576 | Completed | Completed | Completed
aca-new | https://github.com/asiainspection/qcore-apps-descriptors/pull/1585 | Completed | Completed | Completed
user-service-cloud | https://github.com/asiainspection/qcore-apps-descriptors/pull/1581 | Completed | Completed | Completed
e-signature-web | 部署master |  |  | Completed | It's deployed in jenkins. --By Nina Wang

## Release Plan 202400709
Release Plan 202400709
Date
Create & Freeze Release Branch: | Tuesday, July 9, 2024
Release Planned Date: | Friday, July 5, 2024
Project/Repositories | Release Version | Create Release Branch | Deploy Release to PP | Merged Release to Master | Production Deployment | Release/Tagging | Merge Release to Develop | Deploy Develop to PP | Remarks
commons | 1.5.202-SNAPSHOT | [8 empty] | commons=1.5.202-SNAPSHOT
Back End | [9 empty] | Back End=
customer-service | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | customer-service=release-8.77
irp-service | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | irp-service=release-8.77
psi-service | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | psi-service=release-8.77
WQS-service | release-1.0.74 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | WQS-service=release-1.0.74
AIMS-service | release-5.1.7 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | AIMS-service=release-5.1.7
Front End | [9 empty] | Front End=
aca | release-1.12.34 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | aca=release-1.12.34
back-office | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | back-office=release-8.77
backoffice-portal-web | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | backoffice-portal-web=release-8.77
checklist-web | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | checklist-web=release-8.77
parameter-web | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | parameter-web=release-8.77
psi-web | release-8.77 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | psi-web=release-8.77
Public-API | release-1.2.183 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | Public-API=release-1.2.183
AIMS-web | release-5.1.7 | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | AIMS-web=release-5.1.7
EKS services | Release Version | Deployment PR link
aca-new | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1567 | Done
lab-photos | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1564 | Done
exchange-service-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1556 | Done
parameter-service-legacy-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1555 | Done
lt-external-service-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1562 | Done
aca-service-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1568 | Done
search-center-service-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1565 | Done
gi-service-cloud | no need release branch | https://github.com/asiainspection/qcore-apps-descriptors/pull/1607 | Done